What to do, in order

A founder’s step-by-step guide to building a scalable app with Claude Code

This guide goes with the CTO Starter Kit (the cto-starter-kit/ folder). Follow the steps in order and finish each one before starting the next. You don’t need to be technical: Claude Code writes the code, and your job is to decide what to build, check the result and approve each step.

| Step | What | Time |
| --- | --- | --- |
| 1 | Install the tools | About 1 hour |
| 2 | Open the accounts | About 1 hour |
| 3 | Set up the project | About 30 minutes |
| 4 | Fill in the product brief | 1–2 hours |
| 5 | Build in phases with Claude Code | 2–4 weeks |
| 6 | Follow the routine after every phase | 30 minutes per phase |

# Step 1: Install the tools

Install these in this order, from the official websites only. To check each one, open the Terminal (on a Mac: Terminal; on Windows: Ubuntu, after installing WSL2) and type the command in the last column.

| # | Tool | Where to get it | Check it works |
| --- | --- | --- | --- |
| 1 | VS Code (code editor) | code.visualstudio.com | Open the app |
| 2 | Git (version history) | git-scm.com | git --version |
| 3 | Node.js, the LTS version | nodejs.org | node --version |
| 4 | pnpm (installs code libraries) | Run corepack enable | pnpm --version |
| 5 | Docker Desktop (runs the database on your computer) | docker.com | docker --version |
| 6 | Claude Code | claude.com/claude-code | claude --version |
| 7 | GitHub CLI (optional) | cli.github.com | gh --version |

Windows users Install WSL2 (Ubuntu) first, then install everything else inside it. Claude Code and Docker work best that way.

When you first open the project in VS Code, it will offer to install the recommended extensions. Click Install All.

# Step 2: Open the accounts

Use one business email address and turn on 2-factor authentication on every account.

| ☐ | Account | What it’s for | Needed by | Free tier? |
| --- | --- | --- | --- | --- |
| ☐ | GitHub | Stores your code | Now | Yes |
| ☐ | Claude (Pro or Max) | Claude Code | Now | Paid |
| ☐ | Neon | Database (PostgreSQL) | Phase 2 | Yes |
| ☐ | Clerk | Sign-up and login | Phase 2 | Yes |
| ☐ | Upstash | Cache and job queue (Redis) | Phase 3 | Yes |
| ☐ | Vercel | Hosts the website | Phase 7 | Yes |
| ☐ | Railway | Hosts the backend | Phase 7 | Small monthly cost |
| ☐ | Sentry and PostHog | Error alerts and analytics | Phase 7 | Yes |
| ☐ | Cloudflare | Domain name and file storage | Phase 7 | Mostly free |
| ☐ | Resend | Sending emails | When needed | Yes |
| ☐ | Stripe | Taking payments | Phase 8 | Fee per transaction |

Rough cost: about £0–40 a month while you build, and about £50–300 a month with your first few thousand users. Set spending alerts on every account.

Golden rule: keep secrets secret Never paste passwords or API keys into the Claude chat, documents or code. Keys go only in the .env file on your computer (it is never uploaded) and in each hosting provider’s "Environment Variables" settings page.

# Step 3: Set up the project

Type these commands in the Terminal, one line at a time. Lines starting with # are notes for you, so don’t type them.

# Make a project folder and go into it mkdir my-product && cd my-product # Copy everything from cto-starter-kit/ into this folder, then: git init git add . git commit -m "Project kit" # Create a private GitHub repository and upload the files gh repo create my-product --private --source=. --push # Open the project in VS Code code .

# Step 4: Fill in the product brief

Open docs/PRODUCT_BRIEF.md and answer the questions in plain English. This is the most important step, because Claude builds from what you write here.

- Who is it for, and what problem does it solve?

- The 3–5 must-have features for launch (and what you are not building yet)

- The main screens, the data you store, how you make money, and the look and feel

Shortcut: open Claude Code and say: "Interview me one question at a time to fill in docs/PRODUCT_BRIEF.md."

# Step 5: Build in phases with Claude Code

Open the Claude Code panel in VS Code (or type claude in the VS Code terminal). For each phase, open the prompt file, copy it all and paste it into Claude Code. Do one phase at a time.

| ☐ | Phase | Prompt file | What you get |
| --- | --- | --- | --- |
| ☐ | 0. Plan | 00-plan.md | A build plan, data model and screen list for you to approve |
| ☐ | 1. Scaffold | 01-scaffold.md | The project skeleton runs on your computer |
| ☐ | 2. Login and database | 02-auth-and-database.md | Sign-up, login and database tables |
| ☐ | 3. API, cache, jobs | 03-api-cache-jobs.md | The backend "brain", caching for speed, background tasks |
| ☐ | 4. Frontend | 04-frontend.md | All the real screens, mobile-friendly |
| ☐ | 5. Security | 05-security.md | A full security check and fixes |
| ☐ | 6. Tests and CI | 06-testing-ci.md | Automatic checks on every change |
| ☐ | 7. Go live | 07-deploy.md | A test site plus the real site on your domain, with monitoring |
| ☐ | 8. Payments | 08-payments.md | Stripe subscriptions (only if you charge money) |
| ☐ | 9. Scale | 09-scale.md | Load tests and tuning (only once you have real traffic) |

Tip: use Plan mode for big phases Press Shift+Tab in Claude Code to switch to Plan mode. Claude explains what it will do before touching any code. Read the plan, ask questions, then approve it.

# Step 6: The routine after every phase

- Start a fresh session for each phase by typing /clear, so Claude focuses on one job.

- Paste the phase prompt and let Claude work. Read each command it asks permission for, and approve the ones that make sense.

- Test it yourself. Run pnpm dev, open http://localhost:3000 and click around.

- Say: "Run all tests, lint and typecheck. Fix anything failing."

- Type /code-review, then /security-review, to get a second look.

- Say: "Explain what you changed in plain English, and update CLAUDE.md and docs/ROADMAP.md."

- Say: "Commit this phase with a clear message and push to GitHub."

- Tick the phase off in the table above and move on to the next one.

If something goes wrong Paste the error message into Claude Code and say: "Find the root cause and fix it." To undo everything since the last good point, say: "Revert to the last commit." Committing after every phase is what makes this possible.

# Optional fast start: Lovable

If you want something to show real users within days, you can build the first version in Lovable instead of Steps 3–5. Connect Lovable to GitHub on day one so you own the code. Paste your product brief into its project knowledge. Later, open the same GitHub repository in VS Code and continue with Claude Code, using phases 5–9 to add security, tests, monitoring and scale.

Skip Lovable and use this guide from the start if your product is backend-heavy from day one: marketplaces, payments, real-time features, AI pipelines, or sensitive health or financial data.

# Get a human for these

| Area | Who | When |
| --- | --- | --- |
| Brand, logo and user testing | A designer (freelance is fine) | Before the public launch |
| Security review or penetration test | A security firm or experienced freelancer | Before you hold sensitive data or take real payments |
| Privacy policy, terms and GDPR | A lawyer (templates are OK at first) | Before launch |
| Architecture check | A senior engineer, 2–4 hours paid | After phase 3 |
| Company, tax and accounts | An accountant | Before taking money |